## Blad1
Context Project: Virtual Humans for Serious Games Group: VH1
Sprint Plan reflection # 5
User Story | Task | Task Assigned To | Estimated Effort per Task | Actual Effort in hours | Done? | Notes
A user needs a virtual human for tygron | Implement basic agent | Karim, Noor | 8 points | 3 hours | Yes | We couldn't start untill Friday
| Implement basic percepts | Roy | 5 points | 2 hours | Yes | There aren't many percepts to implement yet
| Analyse new evironment | Karim | 3 points | 1 hour | Yes
A User needs a strategy | Analyse Game Session developers | All | 6 points | 5 hours | Yes
| Game Session Students | All | 12 points | 2 hours | Yes | We focused mainly on the differences with our strategy
| Create strategy plan for developers | Noor, Chantal, Paul | 6 points | 4 hours | Yes
Main Problems Encountered
| Desciption | Solution
| We couldn't start coding untill Friday, because we had to wait until the other group had implemented the actions | We worked on our game sessions and report
| Once we started coding there were only 2 percepts and 2 actions | We implemented the basics and put other ideas in comments