## Blad1
Context Project: Virtual Humans for Serious Games Group: VH1
Sprint Plan reflection # 3
User Story | Task | Task Assigned To | Estimated Effort per Task | Actual Effort in hours | Done? | Notes
A User needs a test map to play the game | Create software design | Everyone | 7 Points | 4 hours | Yes | Including a lot of consulting with group 3 as to what they think they can achieve in this project
| Create basic percept handlers | Karim, Paul, Roy | 4 Points | 3 hours | Yes
| Update list of needed percepts. | Noor | 1 Points | 1 hour | Yes | We will keep updating the list as we think of more percepts
| Update test map | Chantal | 2 Points | 2 hour | Yes | We had to recreate the map
| Update product plan | Noor | 1 Points | 1,5 hours | Yes
| Start with basic test | Chantal | 2 Point | 1,5 hours | Yes
Main Problems Encountered
| Desciption | Solution
| The Tygron server crashed, so our entire map was deleted. | We had to recreate the entire map
| We don't know what percepts we can expect (so how difficult our percepts can be) | Frequent meetings with group 3