## Sheet1
Context Project: Virtual Humans for Serious Games Group: VH1
Sprint Plan # 1
User Story | Task | Task Assigned To | Estimated Effort per Task
A User needs a test map to play the game | Analyse Stakeholders | Roy, Chantal | 5 points
| Create Steakholders | Noor | 0.5 point
| Create Map | Paul, Karim | 4 points
| Analyse Map | Karim, Noor | 3 points
| Appoint meeting with Tygron | Paul | 0.1 point
| Meeting with Tygron to check map | Paul, Karim | 2 point