## Blad1
Context Project: Virtual Humans for Serious Games Group: VH2
Sprint Plan reflection # 7
User Story | Task | Task Assigned To | Estimated Effort per Task | Actual Effort in hours | Done? | Notes
A user needs a virtual human for tygron | Put emotions into the strategy | Karim | 1 point | 1 hour | No | Had a meeting with group 3, but they are almost finished. They just need to implement the emotion into the beliefs
A User needs a strategy | Start implementing housing strategy | Noor, Paul | 6 points | 8 hours | Yes
| Start implementing company strategy | Roy, Chantal | 6 points | 8 hours | Yes | We focused mainly on the differences with our strategy
Yes
| Update standard events | Karim | 4 points | 6 hours | yes
Main Problems Encountered
| Desciption | Solution
Environment | Environment update was wrong | Used an old environment for now, group 1 will fix this
Build | The build action has no offices | Told group 1, for now use the build house instead of offices
Self | The virtual human doesn't now which stakeholder he is | Use a placeholder belief
Permits | Still have no permits percept | Told group 1 to priotitize this to fix it. No solution yet.