## Blad1
Context Project: Virtual Humans for Serious Games Group: VH1
Sprint Plan reflection # 5
User Story | Task | Task Assigned To | Estimated Effort per Task | Actual Effort in hours | Done? | Notes
A user needs a virtual human for tygron | Code cleanup | Paul | 4 points | 1 hours | Yes | Faster than expected
A User needs a strategy | Game Session devolpers | All | 10 points | 8 hours | Yes
| Game Session Students | All | 12 points | - | No | Had a meeting for SE during the time we planned to do this.
| Create strategy plan | Noor, Chantal, Roy | 15 points | 2 hour | Partly | Only with one session
A User needs a test map to play the game | Update descriptions of the map | Karim | 3 poins | 2 hours | Yes
Main Problems Encountered
| Desciption | Solution
| The time we planned with people to do a game session, was during a SE meeting. | We rescheduled an new time
| Limited time (Examens, meetings) | Sheduled time in weekend