## Sheet1
Context Project: Virtual Humans for Serious Games Group: VH1
Sprint Plan reflection # 1
User Story | Task | Task Assigned To | Estimated Effort per Task | Actual Effort in hours | Done? | Notes
A User needs a test map to play the game | Analyse Stakeholders | Roy, Chantal | 5 points | 4 hours | Yes
| Create Steakholders | Noor | 0.5 point | 1 hours | Yes
| Create Map | Paul, Karim | 4 points | 2 hours | Yes
| Analyse Map | Karim, Noor | 3 points | 6 hours | Yes | Group effort
| Appoint meeting with Tygron | Paul | 0.1 point | 0.2 hour | Yes
| Meeting with Tygron to check map | Paul, Karim | 2 point | - | No | Wednesday 6 may
Main Problems Encountered
| Desciption | Solution
Problem 1 | Meeting later than expected | Agreed