## Sheet1
Context Project: Virtual Humans for Serious Games Group: VH1
Sprint Plan reflection # 2
User Story | Task | Task Assigned To | Estimated Effort per Task | Actual Effort in hours | Done? | Notes
A User needs a test map to play the game | Meet with Tygron to talk about the map. | Karim, Paul, Noor | 2 Points | 1.5 hours | Yes
| Prepare meeting with Tygron. | Karim, Paul | 0,5 Points | 0.5 hours | Yes
| Make list of needed percepts. | Roy | 1 Points | 2 hours | Yes | Meeted with group port-java, to check
| Learn about EIS. | Roy | 1 Points | 3 hours | Yes | EIS is not really usefull / not sure
| Finish map with tips from Tygron. | Everyone | 2 Points | 5 hours | Yes | Change profit of housing
| Work on the deliverables. | Chantal | 1 Point | 1 hour | Yes
Main Problems Encountered
| Desciption | Solution