## Blad1
Context Project: Virtual Humans for Serious Games Group: VH2
Sprint Plan reflection # 8
User Story | Task | Task Assigned To | Estimated Effort per Task | Actual Effort per Task | Done? | Notes
A user needs a virtual human for tygron | Put emotions into the strategy | Karim | 2 points | 5 hours | No | Noor took this over and added emotions. A complication accored with modules (see problems section)
A User needs virtual human with a strategy | Add permits for housing and company | Karim, Roy, Chantal | 8 points | 50 hours | Yes | Team contribution + more hours for debugging. Permits added newe strategies
| Fix placeholders | Paul | 4 points | 8 hours | Yes
| Clean code | Roy | 1 point | 2 hours | Yes
| Create scenario tests | Noor, Chantal, Paul | 10 points | 3 hours | No | Problem with test2g files (see problem section
Main Problems Encountered
| Desciption | Solution
Test | The atstart and adend testconditions did not work propperly, everything we had to test had to do with differences throughout the game sessions. I | We manually tested every scenario. This way we are sure the code works.
Build | The build actions was a problem. It did not work. This made running the code impossible. | Group 1 fixed this error very fast (within a day).
Gamygdala | The Gamygdala port was only avaible from Wednesday on, because on Wednesday we were finally able to work with the propper environment we had to do a lot of work in a very short timespam | Implementing the real basic parts of emotions.